## Estimation
Effort Estimation for Project: CSV File Comparison
The CSV File Comparison Tool is designed to efficiently compare two CSV files, identify discrepancies, and generate detailed reports. The tool focuses on comparing data integrity between two files based on primary key columns and data values. It is equipped with functionalities to handle missing, extra, or duplicate rows and columns and allows users to easily validate and document differences between datasets.
Section | Task | Description | Estimated Effort (hrs)
1. Environment Setup | 1.1. Environment Setup | Set up the working environment: install necessary libraries, set up virtual environment. | 1
| 1.2. Requirements Gathering | Collect and analyze the requirements of the project. | 1
| 1.3. Setup Configuration File | Prepare the config.ini file for input parameters. | 1
2. Config and Setup Input Parameters | 2.1. Define Input File Paths | Identify and set the file paths in the configuration for the CSV files. | 1
| 2.1.1. Create config entries for file1_path | Add an entry for file1_path in the config.ini. | 0.5
| 2.1.2. Create config entries for file2_path | Add an entry for file2_path in the config.ini. | 0.5
| 2.1.3. Verify file existence | Validate that the files exist using os.path.exists(). | 0.5
| 2.2. Define Primary Key Columns | Set the primary key columns in the config.ini. | 1
| 2.2.1. Add config entries for primary_key_columns | Define primary key column names and add to config.ini. | 0.5
| 2.2.2. Validate Primary Key Columns | Check if primary key columns exist in the CSV files. | 0.5
| 2.3. Configure Output File Path | Define and verify the output file path. | 1
| 2.3.1. Add config entry for output_file | Specify the output path for the comparison report in config.ini. | 0.5
| 2.3.2. Verify output file directory | Ensure the output directory exists or create it. | 0.5
| 2.4. Validate Data Integrity | Perform data validation on the input files. | 1.5
| 2.4.1. Check column existence in file1 | Ensure all required columns are present in file1. | 0.5
| 2.4.2. Check column existence in file2 | Ensure all required columns are present in file2. | 0.5
| 2.4.3. Validate data format in file1 | Ensure that data types and formats are correct in file1. | 0.5
| 2.4.4. Validate data format in file2 | Ensure that data types and formats are correct in file2. | 0.5
3. Code Implementation | 3.1. Implement File Reading Logic | Implement code to read CSV files into pandas DataFrames. | 2
| 3.2. Implement Primary Key Check | Implement logic to check primary key columns in both files. | 2
| 3.3. Implement File Comparison Logic | Compare data between file1 and file2. | 5
| 3.4. Handle Missing/Extra Columns | Implement logic to identify missing/extra columns. | 4
| 3.5. Handle Missing/Extra Rows | Implement logic to detect missing/extra rows in files. | 4
4. Report Generation | 4.1. Generate HTML Report | Implement HTML report generation for differences between files. | 4
| 4.2. Format Report Tables | Format and style tables for displaying differences in the report. | 2
| 4.3. Add Summary Information | Include general comparison information (e.g., missing rows, columns) in the report. | 2
5. Testing & Debugging | 5.1. Unit Testing | Test individual functions for correctness. | 3
| 5.2. Integration Testing | Test end-to-end functionality of the entire tool. | 3
| 5.3. Error Handling | Implement proper error handling and validation checks. | 2
6. Issue Fixing & Debugging | 6.1. Debug File Path Issues | Resolve issues related to file path configurations. | 1
| 6.2. Debug Data Format Issues | Handle issues with data formats in input files. | 2
| 6.3. Debug Comparison Logic | Fix bugs in the file comparison logic. | 2
7. Final Review & Documentation | 7.1. Code Review | Review the code for any potential improvements. | 2
| 7.2. Documentation | Document the entire process: how to configure, run, and troubleshoot the program. | 2
Total Efforts |  |  | 55
Buffer 10% |  |  | 5.5
Total Effort (with Buffer): |  |  | 60.5