## Sheet1
Section | Task | Description | Estimated Effort (hrs)
1. Environment Setup | 1.1. Environment Setup | Set up the working environment: install necessary libraries, set up virtual environment. | 1
| 1.2. Requirements Gathering | Collect and analyze the requirements of the project. | 1
| 1.3. Setup Configuration File | Prepare the config.ini file for input parameters. | 1
2. Config and Setup Input Parameters | 2.1. Define Input File Paths | Identify and set the file paths in the configuration for the CSV files. | 1
| 2.1.1. Create config entries for file1_path | Add an entry for file1_path in the config.ini. | 0.5
| 2.1.2. Create config entries for file2_path | Add an entry for file2_path in the config.ini. | 0.5
| 2.1.3. Verify file existence | Validate that the files exist using os.path.exists(). | 0.5
| 2.2. Define Primary Key Columns | Set the primary key columns in the config.ini. | 1
| 2.2.1. Add config entries for primary_key_columns | Define primary key column names and add to config.ini. | 0.5
| 2.2.2. Validate Primary Key Columns | Check if primary key columns exist in the CSV files. | 0.5
| 2.3. Configure Output File Path | Define and verify the output file path. | 1
| 2.3.1. Add config entry for output_file | Specify the output path for the comparison report in config.ini. | 0.5
| 2.3.2. Verify output file directory | Ensure the output directory exists or create it. | 0.5
| 2.4. Validate Data Integrity | Perform data validation on the input files. | 1.5
| 2.4.1. Check column existence in file1 | Ensure all required columns are present in file1. | 0.5
| 2.4.2. Check column existence in file2 | Ensure all required columns are present in file2. | 0.5
| 2.4.3. Validate data format in file1 | Ensure that data types and formats are correct in file1. | 0.5
| 2.4.4. Validate data format in file2 | Ensure that data types and formats are correct in file2. | 0.5
3. Code Implementation | 3.1. Implement File Reading Logic | Implement code to read CSV files into pandas DataFrames. | 2
| 3.2. Implement Primary Key Check | Implement logic to check primary key columns in both files. | 2
| 3.3. Implement File Comparison Logic | Compare data between file1 and file2. | 5
| 3.4. Handle Missing/Extra Columns | Implement logic to identify missing/extra columns. | 4
| 3.5. Handle Missing/Extra Rows | Implement logic to detect missing/extra rows in files. | 4
4. Report Generation | 4.1. Generate HTML Report | Implement HTML report generation for differences between files. | 4
| 4.2. Format Report Tables | Format and style tables for displaying differences in the report. | 2
| 4.3. Add Summary Information | Include general comparison information (e.g., missing rows, columns) in the report. | 2
5. Testing & Debugging | 5.1. Unit Testing | Test individual functions for correctness. | 3
| 5.2. Integration Testing | Test end-to-end functionality of the entire tool. | 3
| 5.3. Error Handling | Implement proper error handling and validation checks. | 2
6. Issue Fixing & Debugging | 6.1. Debug File Path Issues | Resolve issues related to file path configurations. | 1
| 6.2. Debug Data Format Issues | Handle issues with data formats in input files. | 2
| 6.3. Debug Comparison Logic | Fix bugs in the file comparison logic. | 2
7. Final Review & Documentation | 7.1. Code Review | Review the code for any potential improvements. | 2
| 7.2. Documentation | Document the entire process: how to configure, run, and troubleshoot the program. | 2
8. S3 Integration and File Management | 8.1. Implement S3 Integration | Set up S3 integration to download zip files from the source and destination S3 buckets. | 2
| 8.2. Download Zip Files from S3 | Implement logic to download zip files from both source and destination S3 buckets. | 2
| 8.3. Unzip Files and Move to Folders | Unzip the downloaded files and move them to the appropriate source and destination folders. | 3
9. Parallelism for Large Scale File Processing | 9.1. Implement Parallel File Processing Framework | Set up the parallel processing framework (e.g., concurrent.futures, multiprocessing) for handling large numbers of CSV files. | 3
| 9.2. Implement File Batching for Parallelism | Break down the 50,000 CSV files into smaller batches for parallel processing. | 2
| 9.3. Parallel File Reading and Comparison | Implement parallel file reading and comparison logic to handle 50,000 files efficiently. | 4
| 9.4. Optimize Memory and CPU Usage | Implement optimizations to manage memory and CPU usage for parallel processing of large file sets. | 2
| 9.5. Monitor Parallel Execution | Set up monitoring for the parallel execution to track progress, failures, and time taken for each batch. | 2